## Blad1
Name (Description) | Index | Points | Action Type | Prefabs needed | Explanation (Full description) | Wrong action (Extra)
Make hands wet | 0 | 1 | use | Sink cabinet
Apply soap | 1 | 1 | use, sequenceStep | Soap dispenser
Rub palms together | 2 | 1 | sequenceStep
Rub right palm against | 3 | 1 | sequenceStep
the back of the left hand
Rub palms together | 4 | 1 | sequenceStep
rub crocheted hands | 5 | 1 | sequenceStep
turn thumb in palm | 6 | 1 | sequenceStep
Rub and turn with pinched | 7 | 1 | sequenceStep
together fingers on palms
wash hands with water | 8 | 1 | sequenceStep | Sink cabinet
dry them with | 9 | 1 | sequenceStep | ClothPackage
disposable cloth
turn off tap with cloth | 10 | 1 | sequenceStep | Sink cabinet
fill palm with handalcohol | 11 |  | use, sequenceStep | Alcohol
Rub palms together | 12 | 1 | sequenceStep
Rub right palm against | 13 | 1 | sequenceStep
the back of the left hand
Rub palms together | 14 | 1 | sequenceStep
rub crocheted hands | 15 | 1 | sequenceStep
turn thumb in palm | 16 | 1 | sequenceStep
Rub and turn with pinched | 17 | 1 | sequenceStep
together fingers on palms

## Blad2
Step and index | Issues | Description | Labels | Assign | Epic | release
| Creating scene for hand hygiene |  | medium priority, develop | Dani
| Create action xml for hand hygiene |  | Implement, medium priority, develop | Dani
(0)Making hands wet with water | 3D object for soap dispenser |  | Implement, medium priority, develop | Vittali
| Importing 3D soap dispencer to scene |  | Implement, medium priority, develop | Vittali
| Animation for making hands wet |  | Animation, medium priority | Vittali
| Implementing animation for making hands wet into scene |  | Implement, medium priority, develop | Vittali
| Add step to action xml |  | Implement, medium priority, develop | Vittali
(1 t/m 10) cleaning hands with soap | Making animation sequence for cleaning hands with soap |  | Animation, medium priority | Vittali
| Implementing animation sequence for cleaning hands with soap in scene |  | Implement, medium priority, develop | Vittali
| Creating animation sequence xml for cleaning hands with soap |  | Implement, medium priority, develop | Dani
| Adding animation sequence steps in the xml for cleaning hands |  | Implement, medium priority, develop | Vittali
(11 t/m 17) cleaning hands with alcohol | Making animation sequence for cleaning hands with alcohol |  | Animation, medium priority | Vittali
| Implementing animation sequence for cleaning hands with alcohol in scene |  | Implement, medium priority, develop | Vittali
| Creating animation sequence xml for cleaning hands with alcohol |  | Implement, medium priority, develop | Dani
| Adding animation sequence steps in the xml for cleaning hands |  | Implement, medium priority, develop | Vittali